## 01_BoQ
Item_ID | Work_Package | Category | Budget_GBP
1 | Site Preparation | Groundworks | 250000
2 | Excavation | Groundworks | 400000
3 | Foundations | Structure | 850000
4 | Concrete Frame | Structure | 1600000
5 | Structural Steel | Structure | 1200000
6 | Roof Works | Envelope | 550000
7 | Curtain Wall / Cladding | Envelope | 900000
8 | Electrical Installation | MEP | 950000
9 | Mechanical / HVAC | MEP | 1100000
10 | Plumbing & Drainage | MEP | 500000
11 | Internal Finishes | Finishes | 800000
12 | External Works & Landscaping | External | 400000

## 02_Monthly_Costs
Month | Category | Actual_Cost_GBP
2025-01 | Groundworks | 180000
2025-02 | Groundworks | 260000
2025-03 | Groundworks | 210000
2025-03 | Structure | 300000
2025-04 | Structure | 520000
2025-05 | Structure | 610000
2025-06 | Structure | 700000
2025-06 | Envelope | 180000
2025-07 | Envelope | 260000
2025-07 | MEP | 220000
2025-08 | Envelope | 240000
2025-08 | MEP | 340000
2025-09 | MEP | 420000
2025-09 | Finishes | 150000
2025-10 | MEP | 380000
2025-10 | Finishes | 220000
2025-11 | Finishes | 260000
2025-11 | External | 120000
2025-12 | Finishes | 180000
2025-12 | External | 160000

## 02B_Monthly_Summary
Month | Monthly_Total_GBP | Cumulative_AC_GBP
2025-01 | 180000 | 180000
2025-02 | 260000 | 440000
2025-03 | 510000 | 950000
2025-04 | 520000 | 1470000
2025-05 | 610000 | 2080000
2025-06 | 880000 | 2960000
2025-07 | 480000 | 3440000
2025-08 | 580000 | 4020000
2025-09 | 570000 | 4590000
2025-10 | 600000 | 5190000
2025-11 | 380000 | 5570000
2025-12 | 340000 | 5910000

## 03_Progress
Month | Planned_Progress_Pct | Actual_Progress_Pct
2025-01 | 3 | 2
2025-02 | 8 | 6
2025-03 | 15 | 12
2025-04 | 24 | 20
2025-05 | 34 | 29
2025-06 | 45 | 40
2025-07 | 57 | 51
2025-08 | 68 | 61
2025-09 | 78 | 71
2025-10 | 87 | 81
2025-11 | 95 | 90
2025-12 | 100 | 96

## 04_Project_Info
Field | Value
Project_Name | City Office Block Development
Project_Budget_GBP | 9500000
Start_Month | 2025-01
End_Month | 2025-12
Duration_Months | 12

## 05_EVM
Month | Planned_Progress_Pct | Actual_Progress_Pct | PV_GBP | EV_GBP | AC_GBP | CV_GBP | SV_GBP | CPI | SPI
2025-01 | 3% | 2% | 285000 | 190000 | 180000 | 10000 | -95000 | 1.0556 | 0.66667
2025-02 | 8% | 6% | 760000 | 570000 | 440000 | 130000 | -190000 | 1.2955 | 0.75
2025-03 | 15% | 12% | 1425000 | 1140000 | 950000 | 190000 | -285000 | 1.2 | 0.8
2025-04 | 24% | 20% | 2280000 | 1900000 | 1470000 | 430000 | -380000 | 1.2925 | 0.83333
2025-05 | 34% | 29% | 3230000 | 2755000 | 2080000 | 675000 | -475000 | 1.3245 | 0.85294
2025-06 | 45% | 40% | 4275000 | 3800000 | 2960000 | 840000 | -475000 | 1.2838 | 0.88889
2025-07 | 57% | 51% | 5415000 | 4845000 | 3440000 | 1405000 | -570000 | 1.4084 | 0.89474
2025-08 | 68% | 61% | 6460000 | 5795000 | 4020000 | 1775000 | -665000 | 1.4415 | 0.89706
2025-09 | 78% | 71% | 7410000 | 6745000 | 4590000 | 2155000 | -665000 | 1.4695 | 0.91026
2025-10 | 87% | 81% | 8265000 | 7695000 | 5190000 | 2505000 | -570000 | 1.4827 | 0.93103
2025-11 | 95% | 90% | 9025000 | 8550000 | 5570000 | 2980000 | -475000 | 1.535 | 0.94737
2025-12 | 100% | 96% | 9500000 | 9120000 | 5910000 | 3210000 | -380000 | 1.5431 | 0.96